## Test_Packs
Project No | Project Name | Client | Contractor | Module No | Unit | Test Package No | Rev | Rev Description | Rev Date | Prepared By | Reviewed By | Discipline | Stage | Status
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A1-1 | 1 | CT3-TP-LINECHECK-A1-1 | 0 | ISSUED FOR REVIEW | 2025-02-03 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A1-2 | 1 | CT3-TP-LINECHECK-A1-2 | 0 | ISSUED FOR REVIEW | 2025-02-03 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A1-3 | 1 | CT3-TP-LINECHECK-A1-3 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A1-4 | 1 | CT3-TP-LINECHECK-A1-4 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A2-3 | 1 | CT3-TP-LINECHECK-A2-3 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A2-4 | 1 | CT3-TP-LINECHECK-A2-4 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | A3-3 | 1 | CT3-TP-LINECHECK-A3-3 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | B1-1 | 1 | CT3-TP-LINECHECK-B1-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C1-1 | 1 | CT3-TP-LINECHECK-C1-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C1-2 | 1 | CT3-TP-LINECHECK-C1-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C2-1 | 1 | CT3-TP-LINECHECK-C2-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C2-2 | 1 | CT3-TP-LINECHECK-C2-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C3-1 | 1 | CT3-TP-LINECHECK-C3-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | C3-2 | 1 | CT3-TP-LINECHECK-C3-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | D1-2 | 1 | CT3-TP-LINECHECK-D1-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | D2-1 | 1 | CT3-TP-LINECHECK-D2-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | D2-2 | 1 | CT3-TP-LINECHECK-D2-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | D3-1 | 1 | CT3-TP-LINECHECK-D3-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | D3-2 | 1 | CT3-TP-LINECHECK-D3-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F1-1 | 1 | CT3-TP-LINECHECK-F1-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F1-2 | 1 | CT3-TP-LINECHECK-F1-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F2-1 | 1 | CT3-TP-LINECHECK-F2-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F2-2 | 1 | CT3-TP-LINECHECK-F2-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F3-1 | 1 | CT3-TP-LINECHECK-F3-1 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active
CT3 | UTE PORTOCEM M501 JAC MODULAR PROJECT | CIMTAS (NINGBO) STEEL PROCESSING CO., LTD | BJCHI | F3-2 | 1 | CT3-TP-LINECHECK-F3-2 | 0 | ISSUED FOR REVIEW | 2025-02-07 | Parinya T. | Prawit T. | Piping | Line Check | Active

## Drawings_ISO
Project No | Test Package No | Module No | Unit | Item No | Drawing No | Sheet | Rev | P&ID Reference
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 1 | G1-S4452 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 2 | G1-S4453 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 3 | G1-S4454 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 4 | G1-S4455 | 1 | 3
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 5 | G1-S4456 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 6 | G1-S4457 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 7 | G1-S4458 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 8 | G1-S4459 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 1 | G1-S4460 | 1 | 0
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 2 | G1-S4461 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 3 | G1-S4462 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 1 | G1-S4037 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 2 | G1-S4065 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 3 | G1-S4066 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 4 | G1-S4072 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 5 | G1-S4221 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 6 | G1-S4223 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 7 | G1-S4231 | 1 | 0
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 8 | G1-S4242 | 1 | 0
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 9 | G1-S4463 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 10 | G1-S4464 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 11 | G1-S4465 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 12 | G1-S4466 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 13 | G1-S4467 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 14 | G1-S4468 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 15 | G1-S4469 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 16 | G1-S4470 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 17 | G1-S4471 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 18 | G1-S4472 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 19 | G1-S4473 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 20 | G1-S4474 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 21 | G1-S4475 | 1 | 0
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 22 | G1-S4476 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 23 | G1-S4477 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 24 | G1-S4478 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 25 | G1-S4479 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 26 | G1-S4480 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 27 | G1-S4481 | 1 | 3
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 28 | G1-S4482 | 1 | 3
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 29 | G1-S4483 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 30 | G1-S4484 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 31 | G1-S4485 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 32 | G1-S4486 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 33 | G1-S4487 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 34 | G1-S4488 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 35 | G1-S4489 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 36 | G1-S4490 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 37 | G1-S4491 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 38 | G1-S4492 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 39 | G1-S4493 | 1 | 5
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 40 | G1-S4590 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 1 | G1-S4023 | 1 | 2
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 2 | G1-S4024 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 3 | G1-S4025 | 1 | 1
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 4 | G1-S4342 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 1 | G1-S4038 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 2 | G1-S4062 | 1 | 3
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 3 | G1-S4069 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 4 | G1-S4070 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 5 | G1-S4071 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 6 | G1-S4224 | 1 | 2
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 7 | G1-S4236 | 1 | 3
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 8 | G1-S4495 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 9 | G1-S4496 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 10 | G1-S4497 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 11 | G1-S4498 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 12 | G1-S4499 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 13 | G1-S4500 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 14 | G1-S4565 | 1 | 2
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 15 | G1-S4586 | 1 | 0
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 16 | G1-S4652 | 1 | 1
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 1 | G1-S4028 | 1 | 2
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 2 | G1-S4029 | 1 | 2
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 3 | G1-S4030 | 1 | 0
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 4 | G1-S4587 | 1 | 2
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 5 | G1-S4588 | 1 | 2
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4501 | 1 | 2
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4502 | 1 | 1
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 3 | G1-S4503 | 1 | 0
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 4 | G1-S4504 | 1 | 0
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 5 | G1-S4505 | 1 | 1
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 6 | G1-S4506 | 1 | 2
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 7 | G1-S4225 | 1 | 2
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 8 | G1-S4237 | 1 | 1
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 9 | G1-S4063 | 1 | 1
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 10 | G1-S4073 | 1 | 1
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 11 | G1-S4040 | 1 | 0
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 1 | G1-S4509 | 1 | 2
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 2 | G1-S4510 | 1 | 1
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 3 | G1-S4511 | 1 | 0
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 4 | G1-S4512 | 1 | 0
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 5 | G1-S4513 | 1 | 0
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 6 | G1-S4514 | 1 | 2
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 1 | G1-S4042 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 2 | G1-S4043 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 3 | G1-S4048 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 4 | G1-S4215 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 5 | G1-S4219 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 6 | G1-S4518 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 7 | G1-S4519 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 8 | G1-S4520 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 9 | G1-S4521 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 10 | G1-S4561 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 1 | G1-S4522 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 2 | G1-S4523 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 3 | G1-S4524 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 4 | G1-S4525 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 5 | G1-S4526 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 6 | G1-S4527 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 7 | G1-S4563 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 1 | G1-S4010 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 2 | G1-S4034 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 3 | G1-S4046 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 4 | G1-S4047 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 5 | G1-S4049 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 6 | G1-S4056 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 7 | G1-S4214 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 8 | G1-S4528 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 9 | G1-S4529 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 1 | G1-S4012 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 2 | G1-S4013 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 3 | G1-S4014 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 1 | G1-S4016 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 2 | G1-S4017 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 3 | G1-S4018 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 4 | G1-S4033 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 5 | G1-S4050 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 6 | G1-S4055 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 7 | G1-S4077 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 8 | G1-S4213 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-C3-2 | C3-2 | 1 | 1 | G1-S4002 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 1 | G1-S4530 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 2 | G1-S4531 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 3 | G1-S4532 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 4 | G1-S4533 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 5 | G1-S4534 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 1 | G1-S4080 | 1/1 | 2
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 2 | G1-S4083 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 3 | G1-S4085 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 4 | G1-S4086 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 5 | G1-S4087 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 6 | G1-S4088 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 7 | G1-S4089 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 8 | G1-T4928 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 9 | G1-T4929 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 1 | G1-S4091 | 1/1 | 4
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 2 | G1-S4092 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 3 | G1-S4093 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 4 | G1-S4094 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 5 | G1-S4095 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 6 | G1-S4096 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 7 | G1-S4097 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 1 | G1-S4099 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 2 | G1-S4100 | 1/1 | 3
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 3 | G1-S4101 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 1 | G1-S4102 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 2 | G1-S4103 | 1/1 | 0
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 3 | G1-S4104 | 1/1 | 5
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 4 | G1-S4105 | 1/1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 1 | G1-S4535 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 2 | G1-S4536 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 3 | G1-S4537 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 4 | G1-S4538 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 5 | G1-S4539 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 6 | G1-S4540 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 7 | G1-S4541 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 8 | G1-S4542 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 9 | G1-S4543 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 10 | G1-S4544 | 1 | 1
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 1 | G1-S4545 | 1 | 2
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 2 | G1-S4546 | 1 | 2
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 3 | G1-S4547 | 1 | 2
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 4 | G1-S4548 | 1 | 2
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 5 | G1-S4549 | 1 | 2
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 1 | G1-S4550 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 2 | G1-S4551 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 3 | G1-S4552 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 4 | G1-S4553 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 5 | G1-S4554 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 1 | G1-S4555 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 2 | G1-S4556 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 3 | G1-S4557 | 1 | 2
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 4 | G1-S4558 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 5 | G1-S4559 | 1 | 1
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 6 | G1-S4560 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 1 | G1-S4163 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 2 | G1-S4165 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 3 | G1-S4167 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 4 | G1-S4169 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 5 | G1-S4171 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 1 | G1-S4164 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 2 | G1-S4166 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 3 | G1-S4168 | 1 | 2
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 4 | G1-S4170 | 1 | 1
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 5 | G1-S4172 | 1 | 1

## Punch_Items
Project No | Test Package No | Module No | Unit | Item No | Drawing No | Deficiency Description | Category | Status | Discipline | Punch Stage
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 1 | G1-S4452 | Temporary support to be adjust linner plate to sit on full support no.04 | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 2 | G1-S4453 | To rectify line to non slope. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 3 | G1-S4453 | Bolt / Nut to be torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 4 | G1-S4453 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 5 | G1-S4453 | Support No.01 to be adjust gap 24 mm. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 6 | G1-S4454 | Support No.04 to be add shim plate. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 7 | G1-S4454 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 8 | G1-S4454 | Support to be repair paint. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 9 | G1-S4455 | Support to be tighten. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 10 | G1-S4455 | Temporary support to be sit on support. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 11 | G1-S4455 | Paint to be repair and clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 12 | G1-S4458 | Temporary support to be adjust liner plate | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 13 | G1-S4458 | To be adjust liner plate on support | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 14 | G1-S4458 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 15 | G1-S4456, G1-S4457 | Support not yet install | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 16 | G1-S4456, G1-S4457 | Support not yet install | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 17 | G1-S4456, G1-S4457 | Support not yet install | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 18 | G1-S4456, G1-S4457 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 1 | G1-S4460 | Bolt /Nut To Be Torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 2 | G1-S4460 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 1 | G1-S4461 | Bolt /Nut To Be Torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 2 | G1-S4461 | Temporary Support to be use liner plate full support. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 3 | G1-S4461 | Pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 4 | G1-S4462 | Temporary support to be rectify pipe not sit on support | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 5 | G1-S4462 | Bolt /Nut To Be Torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 6 | G1-S4462 | Paint to be repair and clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 1 | G1-S4023 | Temporary Support 02 U-bolt to be tighten | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 2 | G1-S4023 | Support no 07, 06, 04, 05 To be gap 1 mm | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 3 | G1-S4023 | Temporary Support no 03 to be weld. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 4 | G1-S4023 | Paint to be repair and clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 5 | G1-S4024 | Bolt /Nut to be torque | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 6 | G1-S4024 | Support no 03 liner plate to adjust sit on full support | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 7 | G1-S4024 | Support to be repair paint | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 8 | G1-S4024 | Surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 9 | G1-S4025 | Bolt /Nut to be torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 10 | G1-S4025 | Paint to be repair and clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4501 | TO BE ADJUST SLOPE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4501 | BOLT / NUT TO BE TOURQE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 3 | G1-S4501 | PIPE SURFACE TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 4 | G1-S4501 | INSIDE PIPE TO BE CLEAN AND APPLY VPCI. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4502 | PIPE SURFACE TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4502 | BOLT / NUT TO BE TOURQE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 3 | G1-S4502 | INSIDE PIPE TO BE CLEAN AND APPLY VPCI. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4503 | PIPE SURFACE TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4503 | INSIDE PIPE TO BE CLEAN AND APPLY VPCI. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4504 | SUPPORT NO.2 TO BE CHANGE TO U-BOLT SPECIAL. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4504 | SUPPORT NO.12 TO BE CHANGE TO NORMAL U-BOLT | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 3 | G1-S4504 | PIPE SURFACE TO BE CLEAN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 4 | G1-S4504 | INSIDE PIPE TO BE CLEAN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 5 | G1-S4504 | TO BE INSTALL & WELD. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4505 | BOLT TO BE TOURQE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4505 | MANIFOLDMTO BE ADJUST. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4506 | PIPE SURFACE TO BE CLEAN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4506 | ALL SUPPORT TO BE PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4237, G1-S4063 | PIPE SURFACE TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4237, G1-S4063 | INSIDE PIPE TO BE CLEAN AND APPLY VPCI. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | G1-S4073, G1-S4040 | PIPE SURFACE TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | G1-S4073, G1-S4040 | INSIDE PIPE TO BE CLEAN AND APPLY VPCI. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 1 | G1-S4522 | SUPPORT NO.1 TO BE REPAIR PAINT BEFORE INSULATION. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 2 | G1-S4522 | SUPPORT NO.2 TO BE REPAIR PAINT BEFORE INSULATION. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 3 | G1-S4523 | BOLT / NUT TO BE TOURQE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 4 | G1-S4523 | BOLT / NUT TO BE TOURQE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 5 | G1-S4523 | SUPPORT NO.4 TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 6 | G1-S4524 | SUPPORT NO.2 WASHER TO BE CUT & REMOVE SPRING WASHER. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 7 | G1-S4525 | SUPPORT NO.5 TO BE PAINT AND REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 8 | G1-S4526 | SUPPORT NO.3 TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 9 | G1-S4527 | INTERNAL PIPE TO BE CLEANING. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 10 | G1-S4522 | TEMPORARY SUPPORT TO BE WELD | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 1 | G1-S4012 | CHANGE BOLT / NUT / WASHER OF SPRING SUPPORT IN ACCORDING TO DRAWING. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 2 | G1-S4012 | BASE SUPPORT MISALIGNMENT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 3 | G1-S4013 | BASE SUPPORT MISALIGNMENT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 4 | G1-S4013 | CHANGE BOLT / NUT / WASHER OF SPRING SUPPORT IN ACCORDING TO DRAWING. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 5 | G1-S4014 | LINE MISALIGNMENT TO BE CUT & REWELD INCLUDE PT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 1 | G1-S4530 | Linner plate Damage to be change. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 2 | G1-S4530 | Support to be repair paint before insulation. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 3 | G1-S4530 | U-bolt for temporary support to be tighten. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 4 | G1-S4530 | Temporary support to be touch up paint before insulation. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 5 | G1-S4531 | Support to be repair paint before insulation. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 6 | G1-S4531 | All pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 7 | G1-S4531 | All Weld Joint to be pickling before insulation. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 8 | G1-S4531 | All support to be repair before insulation. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 9 | G1-S4532 | Bolt to be torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 10 | G1-S4532 | All pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 11 | G1-S4533 | Bolt to be torque. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 12 | G1-S4533 | All pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 13 | G1-S4534 | All pipe surface to be clean. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 1 | G1-S4156 | All flange to be torque | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 2 | G1-S4156 | Flange to be adjust alinment | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 3 | G1-S4541 | Change linning plate SS to sit on temporary support fully | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 4 | G1-S4541 | Change linning plate SS to sit on temporary support fully | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 5 | G1-S4542 | U-Bolt for temporary support to be tighten and add linning plate SS | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 1 | G1-S4549 | Plastic gauge valve damage and to be change | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 1 | G1-S4554 | To be add temporary support | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 1 | G1-S4555 | Apply glue on plastic gauge valve | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 2 | G1-S4557 | U-Bolt to be open gab 1 mm | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 3 | G1-S4557 | Missing eaeth bonding | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 4 | G1-S4559 | Missing temporary support | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 1 | G1-S4160 | ALL FLANGE TO BE TORQUE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 2 | G1-S4160 | SUPPORT NO.1 TO BE TIGHTEN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 3 | G1-S4160 | ALL PIPE SURFACE TO BE CLEAN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 4 | G1-S4160 | STRUCTURE FRAME TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 5 | G1-S4160 | EYE BOLTS TO BE INSTALL. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 6 | G1-S4160 | INSIDE PIPE TO BE CLEAN AND BORESCOPE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 7 | G1-S4160 | TEMPORARY SUPPORT TO BE REPAIR PAINT YELLOW. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 8 | G1-S4160 | BOLT / NUT CONNECTION F3-1 TO F3-2 INSTALL NOT PER DWG. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 1 | G1-S4161 | SUPPORT NO.2 TO BE TIGHTEN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 2 | G1-S4161 | ALL PIPE SURFACE TO BE CLEAN. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 3 | G1-S4161 | STRUCTURE FRAME TO BE REPAIR PAINT. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 4 | G1-S4161 | EYE BOLTS TO BE INSTALL. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 5 | G1-S4161 | INSIDE PIPE TO BE CLEAN AND BORESCOPE. | A | OPEN | Piping | Line Check
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 6 | G1-S4161 | TEMPORARY SUPPORT TO BE REPAIR PAINT YELLOW. | A | OPEN | Piping | Line Check

## Content_Checklist
Project No | Test Package No | Module No | Unit | Section No | Section Title | Verify Status
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A1-1 | A1-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A1-2 | A1-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A1-3 | A1-3 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A1-4 | A1-4 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A2-3 | A2-3 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A2-4 | A2-4 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-A3-3 | A3-3 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-B1-1 | B1-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C1-1 | C1-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C1-2 | C1-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C2-1 | C2-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C2-2 | C2-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C3-1 | C3-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-C3-2 | C3-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-C3-2 | C3-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-C3-2 | C3-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-C3-2 | C3-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-D1-2 | D1-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-D2-1 | D2-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-D2-2 | D2-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-D3-1 | D3-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-D3-2 | D3-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F1-1 | F1-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F1-2 | F1-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F2-1 | F2-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F2-2 | F2-2 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F3-1 | F3-1 | 1 | 4 | Punch list | N/A
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 1 | Test pack isometric index | N/A
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 2 | General Arrangement / Isometric Drawing / Pipe Support | N/A
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 3 | Flange joint inspection report | N/A
CT3 | CT3-TP-LINECHECK-F3-2 | F3-2 | 1 | 4 | Punch list | N/A